## Project Tracker
Prototype 1 User Stories
Feb. 7, 2018
Story | Task | Date Requested | Date Accomplished
Create Guidance Office website | Create static homepage | 2018-02-07 | 2018-02-10
| Create basic navigation | 2018-02-07 | 2018-02-10
| Setup basic framework | 2018-02-07 | 2018-02-12
Create Student Information Registry | Make Student Information navigation page | 2018-02-07 | 2018-02-17
| Client Side Data validation | 2018-02-07 | 2018-02-21
| Server Side Data Validation | 2018-02-07 | in-progress - 70%
| Floating entities | 2018-02-07 | 2018-02-18
| Make Student Information add info | 2018-02-07 | 2018-02-21
| Make Student Information info table | 2018-02-07 | 2018-02-22
| Make Student Information update button | 2018-02-07 | in-progress - 10%
Create Test Maker | Create framework | 2018-02-07 | 2018-02-22
| Allow test addition at test maker page | 2018-02-07 | in-progress - 5%
| Allow test editing | 2018-02-07
| Display tests | 2018-02-07
| Test result computations | 2018-02-07

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS